## Sample (fictional)
Meeting Minutes (Sample)
Meeting | Website Renewal Project – Weekly Meeting (No. 5)
Date | Thursday, 12 November 2026
Time | 9:00–9:45 a.m. JST (4:00–4:45 p.m. PST, Wednesday, 11 November)
Location | Online (Zoom)
Chair | Ken Sato
Minute taker | Yuki Tanaka
Attendees | Ken Sato, Yuki Tanaka, Emily Clark, Raj Patel
Absent | Mark Lee
* This is a fictional example. All names, companies and dates are made up.
Purpose
To agree on the launch date and the remaining tasks.
Agenda
1. Review of previous action items
2. Launch date
3. Contact form issue
4. Any other business
Decisions
・It was agreed that the new website will launch on Tuesday, 1 December 2026.
・The team decided to keep the current domain name.
Pending / To be confirmed
・Budget for online ads: TBC. Raj will share the cost estimate at the next meeting.
Action items
Action |  | Owner | Due date
Fix the error on the contact form |  | Raj Patel | Mon, 16 Nov 2026
Send the final page list to the client |  | Yuki Tanaka | Fri, 13 Nov 2026
Prepare the launch checklist |  | Emily Clark | Wed, 18 Nov 2026
Discussion summary
1. Launch date: Emily proposed launching on 1 December. Raj noted that testing would take one week. The team agreed.
2. Contact form: Raj reported that some messages were not being delivered. The cause is still being investigated.
Next meeting
Thursday, 19 November 2026, 9:00 a.m. JST (Zoom)